Project Planning Phase

Project Planning

(Product Backlog, Sprint Planning, Stories, Story points)

| Date | 11 June 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Medi Book-Book a Doctor |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Epic | USN | User Story | Points | Priority | Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Registration | USN-1 | As a user I can register by providing my name, email, password and selecting a role (Patient/Admin). | 3 | High | TM-1 |
| Sprint-1 | User Registration | USN-2 | As a user I will be redirected to my role-specific dashboard after successful registration. | 2 | High | TM-1 |
| Sprint-1 | User Login | USN-3 | As a user I can log in using my email and password and receive a JWT token. | 2 | High | TM-2 |
| Sprint-1 | User Login | USN-4 | As a user I am automatically redirected to /login if my token expires. | 1 | High | TM-2 |
| Sprint-2 | Doctor Browsing | USN-5 | As a patient I can browse all approved doctors and filter by specialty or search by name. | 3 | High | TM-3 |
| Sprint-2 | Doctor Browsing | USN-6 | As a patient I can view a doctor's full profile including fee, hospital, location and experience. | 2 | High | TM-3 |
| Sprint-2 | Appointment Booking | USN-7 | As a patient I can select a date from the next 5 days and a time slot from available options. | 3 | High | TM-1 |
| Sprint-2 | Appointment Booking | USN-8 | As a patient I can choose In-Person or Video, write a reason, and upload documents. | 3 | High | TM-2 |
| Sprint-2 | Appointment Booking | USN-9 | As a patient I can review my booking summary and confirm the appointment. | 2 | High | TM-2 |
| Sprint-3 | Patient Dashboard | USN-10 | As a patient I can view upcoming and past appointments in a tabbed dashboard. | 3 | High | TM-3 |
| Sprint-3 | Patient Dashboard | USN-11 | As a patient I can cancel a pending appointment from my dashboard. | 2 | Medium | TM-3 |
| Sprint-3 | Notifications | USN-12 | As a patient I receive in-app notifications when my appointment is confirmed or completed. | 3 | High | TM-2 |
| Sprint-3 | Doctor Dashboard | USN-13 | As a doctor I can view all incoming appointment requests and confirm or reject them. | 3 | High | TM-1 |
| Sprint-3 | Doctor Dashboard | USN-14 | As a doctor I can add visit notes and mark an appointment as completed. | 2 | High | TM-1 |
| Sprint-4 | Apply as Doctor | USN-15 | As a patient I can submit an application to become a doctor by filling a professional details form. | 2 | Medium | TM-4 |
| Sprint-4 | Admin Dashboard | USN-16 | As an admin I can view all pending doctor applications and approve or reject them. | 3 | High | TM-4 |
| Sprint-4 | Admin Dashboard | USN-17 | As an admin I can view all registered users and toggle their active status. | 2 | Medium | TM-4 |
| Sprint-4 | Admin Dashboard | USN-18 | As an admin I can view platform statistics and all appointments across the system. | 2 | Medium | TM-4 |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Points | Duration | Start Date | End Date (Planned) | Points Completed | Actual Release |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 8 | 5 Days | 01 Jun 2025 | 05 Jun 2025 | 8 | 05 Jun 2025 |
| Sprint-2 | 13 | 7 Days | 06 Jun 2025 | 12 Jun 2025 | 13 | 12 Jun 2025 |
| Sprint-3 | 13 | 7 Days | 13 Jun 2025 | 19 Jun 2025 | 13 | 19 Jun 2025 |
| Sprint-4 | 9 | 5 Days | 20 Jun 2025 | 24 Jun 2025 | 9 | 24 Jun 2025 |

Total Story Points: 43  |  Total Duration: 24 Days |  Average Velocity: ~10.75 points per sprint

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)